## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2255-SWEN-261-02-5E-YourLocalCupboard
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am logged in on the u-fund site when I am not on the Home page then I must see a means to navigate to the Home page. | Pass | NS 4/7
| Given that I am not on the Home page when I choose the Home page then I am taken to the Home page. | Pass | NS 4/7
| Given that I am on the Home page when there are needs in the cupboard then I see each need and its details. | Pass | RG 3/31
| Given that I am on the Home page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | RG 3/31
Login : As a user I want to enter a username and password so that I can access the system. | Given I am on the login page when I login with username admin and admin password, then I should access the admin acount. | Pass | RG 3/31
| Given I am a helper on the login page when I login with my specific username/password then I should access my helper account. | Pass | RG 3/31
| Given I am on the login page when I login with incorrect credentials then I should see an error message. | Pass | RG 3/31
Logout: As a User I want to log out so that I can return to my work later and know that it is securely stored on the server. | Given I am logged in to an account when I click the logout button then I should be logged out of my account. | Pass | RG 3/31
| Given I am logged out when I access the site then I should not be able to access information related to an account. | Pass | JA, I would like it if we automatically routed to /login.
Create Account: As a Helper, I want to create an account so that I can login to donate/request food. | Given I am a helper when I try create an account then I should be able to create an account by entering a username and password | Pass | JA, I would like a password confirmation field.
| Given I am a helper when I try to create an account with an invalid password then the account should not be created and I should receive an error message. | Pass | EM - There could be another error messgae emphasizing what the user has done wrong when they press the submit button when entering invalid username or password. JA, I would like the error message to be more apparent, maybe a red
Pledge Basket Add Need: As a helper, I want to add a pledge to my basket in order to fulfill a need | Given I am a helper on the /home page, when I try to add a pledge for a specific need, the system should let me enter the details of the pledge. | Pass | EM - You should not be able to add a pledge with quantity 0 or price 0. JA, /home/needs does not exists. It appears that needs are displayed on /home page.
As a helper I want to see a list of needs so that I choose what to contribute to. | Given I am a helper on the home page, when I have entered the details of a new pledge and hit 'add to basket', the new pledge should be added to my basket with the right details. | Pass | RG 3/31
Pledge Basket Delete Need: As a helper, I want to be able to remove a need from my basket so that I can change my mind before checkout. | Given I am a User when I remove a pledge from my Pledge Basket then I the system should remove that pledge. | Pass | EM - Is it best that the user is kicked back to the homepage after removing a need from their funding basket. If a user is about to "pledge" which would be over the completion of the needed amount then the user should be notified
PledgeBasket Archive Need: As a Food Ban k, I want to be able to see recently deleted needs, so that I can get it back in case it was a mistake/misclick. | Given I am logged in as an admin, when I delete a need, I expect it to show up in my archive page. | Pass | YL 4/7
| Given I am in my archive page, When I click on the restore button, I expect that need to reapear in my need list. | Pass | YL 4/7
| Given I am in my archive page, when I click on the delete forever button, I expect a reconfirmation and two choices to either delete forever or cancel | Pass | YL4/7
| Given I am a Helper, when a need in my basker is archived, I expect to be notified and the pledge be deleted. | Pass | YL 4/7
Basket Persistance: As a Helper, I want to save my Basket so that I can return to it later and know that it is securely stored on the server. | Given I am a User when I add pledges to my basket then I expect them to be there if I login/logout or if the server restarts | Pass | RG 3/31
Review Basket: As a Helper, I want to review my basket at checkout so that I can be sure I am funding the pledges I intend to. | Given I am a User when I request to review my basket at checkout then I expect a complete list of them. | Pass | EM - A nice addition would be to be able to check out each need individually
Get Pledge Basket: As a helper, I want to view my pledge basket so that I can see all the pledges I have added. | Given I am a helper when I navigate to my pledge basket then I should see a list of all pledges I have added. | Pass | RG 3/31
| Given I am a helper when my basket is empty then I should see a message or indication that my basket has no pledges. | Pass | NS 4/7
| Given I am a helper when I view my basket then I should see the details of each pledge including need name and amount. | Pass | RG 3/31
Pledge Basket Remove: As a helper, I want to be able to remove a pledge from my basket so that I can change my mind before checkout. | Given I am a helper with pledges in my basket when I choose to remove a specific pledge then it should be removed from my basket. | Pass | EM - Again should this take the user back to the helper homepage
| Given I am a helper after removing a pledge when I view my basket then the removed pledge should no longer appear in the list. | Pass | RG 3/31
Pledge Basket Privacy: As a helper, I want my pledge basket to be private so that other users cannot see my personal contributions. | Given I am a helper when another logged-in user accesses the site then they should not be able to view my pledge basket contents. | Pass | RG 3/31
| Given I am a helper when I am logged out then my pledge basket contents should not be accessible to anyone. | Pass | RG 3/31
| Given I am a helper when I log back in then my private basket should be visible only to me. | Pass | RG 3/31
Cupboard Checkout Update: As a helper, I want to checkout my basket so that my pledges are submitted and recorded by the cupboard. | Given I am a helper with pledges in my basket when I proceed to checkout then my pledges should be submitted to the cupboard. | Pass | Should you be able to checkout a need individually
| Given I am a helper who has completed checkout when I view my basket then it should be empty. | Pass | The application does not notify the user
Client Aesthetic: As a user, I want a visually appealing and consistent interface so that I can navigate the site comfortably. | Given I am a user when I access the site then the layout should be clean, organized, and professional. | Pass | RG 3/31, opinionated story but I think it passes
| Given I am a user on any page when I view the site then colors, fonts, and styling should be consistent across all pages. | Pass | RG 3/31
| Given I am a user when I navigate between pages then transitions and UI elements should behave predictably. | Pass | RG 3/31
Need Description Form/Storage: As a helper, I want to see a description for each need so that I understand what I am contributing to. | Given I am a helper on the Home page when I view a need then I should see a detailed description of that need. | Pass | GG 4/7
| Given I am an admin when I create or edit a need then I should be able to add or update a text description for the need. | Pass | GG 4/7
| Given I am an admin when I save a need with a description then the description should persist and be visible to helpers. | Pass | GG 4/7
Ask Harold Need Description Generator: As a user, I want an AI to generate a description for a need so that I can better understand what contributions are needed. | Given I am viewing a need when I request a description from Harold then an AI-generated description should appear for that need. | Pass | GG 4/7
| Given Harold has generated a description when I view the need then the description should be relevant and informative for that specific need. | Pass | GG 4/7
Ask Harold Need Icon Generator & Persistence: As a user, I want AI-generated icons for needs so that I can visually identify needs more easily and icons persist between sessions. | Given I am viewing a need when Harold generates an icon for it then a relevant icon should be displayed alongside that need. | Pass | GG 4/7
| Given an icon has been generated for a need when I return to that need in a later session then the icon should still be displayed. | Pass | GG 4/7
| Given an icon has been generated when other users view the same need then they should also see the persisted icon. | Pass | GG 4/7
Food Bank Registration Screen w/ Location Picking: As a food bank representative, I want to register my food bank with a location so that donors can find me on the platform. | Given I am a food bank representative when I register my food bank then I should be able to specify my physical location. | Pass | GG 4/7
| Given I am registering a food bank when I pick a location using the location picker then my selected location should be saved with my registration. | Pass | GG 4/7
| Given I have registered a food bank when donors browse the site then my food bank should appear with its correct location. | Pass | GG 4/7
User View Needs by Food Bank/Location Area: As a helper, I want to view needs filtered by food bank or location area so that I can contribute to needs near me. | Given I am a helper when I filter needs by location area then I should only see needs from food banks in that geographic area. | Pass | GG 4/7
| Given I am a helper when I select a specific food bank then I should see only the needs associated with that food bank. | Pass | GG 4/7, can filter by specific Food Bank
| Given I am a helper when no needs exist for the selected location or food bank then the search list should be empty. | Pass | GG 4/7